## PLATFORM_PLUS
Implementation Project Plan - Core
Please feel free to customize this template to match your company's needs & resources
| Pre-Reqs: | Task Complete
| Ensure your Cloud directory domain matches SAML application UID's and emails (if applicable) | FALSE
| Obtain administrative credentials for Applicaitons to enable SCIM integration (if applicable) | FALSE
| Obtain administrative credentials for HRIS (if applicable) | FALSE
| Obtain credentials for Super Admin (GWS) and-or Global Admin (MS 365) (if applicable) | FALSE
| Task Name | Documentation | Admin Portal URL | Task Owner | Task Complete | Task Start Date | Task Complete Date | Notes
| Preparation Work |  |  |  |  | MM/DD/YY | MM/DD/YY
0.01 | Get Access to JumpCloud Admin Portal with Administrator Account | JCU: Intro to Admin Portal | JumpCloud Admin Portal |  | FALSE
0.02 | Bookmark the JumpCloud Admin Portal |  |  |  | FALSE
0.03 | Log into Admin Portal with your JumpCloud Admin Account | JumpCloud Admin Portal Login |  |  | FALSE
0.04 | Access Support KB Portal | JumpCloud Support Center | Support Page |  | FALSE
0.05 | Learn how to create a Support Case with JumpCloud in the Admin Portal | Contacting JumpCloud Support | Submit a Support Ticket |  | FALSE
0.06 | Find Organizational Settings | Admin Portal Org Settings | Org Settings |  | FALSE
0.07 | Name your Organization |  |  |  | FALSE
0.08 | Enter the primary admin's contact information |  |  |  | FALSE
0.09 | Upload company logo |  |  |  | FALSE
0.1 | Review the JumpCloud Admin portal layout |  |  |  | FALSE
0.11 | Educate Users on upcoming implementation of JumpCloud | Email templates for Educating New Users |  |  | FALSE
Preparation Milestones Complete
Phase 1 - Tour the JumpCloud Admin Portal
Pre | Inform Company that you will be implementing JumpCloud. Let them know what it is and how it affects them. | Email templates for Educating New Users |  |  | FALSE
1 | Find User Security Settings | User Security Settings | User Security Settings |  | FALSE
1.1 | Configure password complexity |  |  |  | FALSE
1.2 | Configure password aging |  |  |  | FALSE
1.3 | Configure password lockout |  |  |  | FALSE
1.4 | Configure User Portal Session Duration |  |  |  | FALSE
1.5 | Configure MFA Settings & Options | JumpCloud MFA Guide | MFA Configurations |  | FALSE
1.6 | Invite IT staff as JumpCloud administrators (Administrator accounts are separate from User accounts) | Managing JumpCloud Admins |  |  | FALSE
Phase 1 Milestones Complete
Phase 2 - Users
Pre | Inform Users that you are starting the project by creating JumpCloud Accounts for them. | Email templates for Educating New Users |  |  | FALSE
2 | Obtain cloud directory Admin credentials |  |  |  | FALSE
2.1 | Navigate to Cloud Directories Menu | Office 365 G Suite | Cloud Directories |  | FALSE
2.1.1 | Create a new Directory, and provide a display name |  |  |  | FALSE
2.1.2 | Utilize the cloud directories Admin credentials already obtained to sync with JumpCloud |  |  |  | FALSE
2.1.3 | Navigate to Users in JumpCloud Admin portal |  |  |  | FALSE
2.1.4 | Import Users (several different options) | Import Office 365 User Import G Suite User Import Users via CSV |  |  | FALSE
2.2 | Navigate to Users menu in JumpCloud Admin portal |  | Users |  | FALSE
2.2.1 | Bind the User to their Directory Sync. JumpCloud will become authoritative over their synced M365/GWS account. | Binding user to Office 365 Binding user to G Suite |  |  | FALSE
2.2.2 | The user will receive a Get Started email requiring them to set a JumpCloud password, in turn updating thier cloud directory password |  |  |  | FALSE
2.2.3 | The user will become active within JumpCloud once they've set a password from their welcome email in the previous step. |  |  |  | FALSE
2.3 | Create User Groups to align with org layout and requirements | Getting Started: Groups | User Groups |  | FALSE
2.3.1 | Assign Users to their respective User Group(s) |  |  |  | FALSE
2.4 | Enroll Users in MFA | Configuring MFA for User Accounts | MFA Configurations |  | FALSE
Phase 2 Milestone Complete
Phase 3 - SSO
Pre | Notify Users that you are going to be redirecting all logins from X applications to JumpCloud starting on X date. | Email templates for Educating New Users |  |  | FALSE
Pre | Ensure all users that need the application are imported and activated with a valid password before starting anything within the SSO Phase |  | Users |  | FALSE
3 | Configure SAML app integration (if applicable) | Getting Started: Applications | SSO |  | FALSE
3.1 | Configure JIT app integration (if applicable) | SAML Supported JIT Provisioning |  |  | FALSE
3.2 | Configure SCIM app integration (if applicable) | JumpCloud Identity Management Connectors |  |  | FALSE
3.3 | Bind User Groups to the SSO Application(s) | Getting Started: Applications |  |  | FALSE
3.4 | Repeat for all of your companies SSO Applications |  |  |  | FALSE
Phase 3 Milestone Complete
Phase 4 - RADIUS
Pre | Notify Users that X network (Wifi or VPN) will begin to use their JumpCloud credentials on X date | Email templates for Educating New Users |  |  | FALSE
4 | Create a RADIUS endpoint in JumpCloud | Getting Started: RADIUS | RADIUS |  | FALSE
4.1 | Point Wifi, VPN, or RADIUS-enabled Networking devices to newly created RADIUS endpoint. |  |  |  | FALSE
4.2 | Add User Groups to RADIUS endpoint to allow users network access. |  |  |  | FALSE
4.3 | Enable MFA for RADIUS networks (if applicable) | TOTP MFA for RADIUS |  |  | FALSE
4.4 | Configure RADIUS Reply Attributes for User Groups (if applicable) | Configure RADIUS Reply Attributes |  |  | FALSE
Phase 4 - Milestone Complete
Phase 5 - LDAP & Samba
Pre | Notify Users that X resources will begin to use their JumpCloud credentials on X date | Email templates for Educating New Users |  |  | FALSE
5 | Create LDAP Service Account with BindDN privileges | Create an LDAP Binding User | Users |  | FALSE
5.1 | Configure LDAP | Configuring JumpCloud LDAP | LDAP |  | FALSE
5.2 | Configuring Samba (if applicable) | Enabling Samba Support with LDAP |  |  | FALSE
5.3 | Creating LDAP Groups | Creating LDAP Groups | User Groups |  | FALSE
5.4 | Configure your LDAP resource (i.e. a NAS or legacy application) to use JumpCloud's LDAP Server |  | LDAP |  | FALSE
Phase 5 Milestone Complete
Phase 6 - Insights
6 | Familiarize yourself with Directory Insights Logging | JumpCloud's Directory Insights | Directory Insights |  | FALSE
6.1 | Export Insights data into SIEM tools (optional if using a 3rd party SIEM) | Directory Insights and AWS Lambda to S3 |  |  | FALSE
Phase 6 Milestone Complete