## PLATFORM_PLUS
Implementation Project Plan - SSO + Device Management
Please feel free to customize this template to match your company's needs & resources
| Pre-Reqs: | Task Complete
| Ensure your Cloud directory domain matches SAML application UID's and emails (if applicable) | FALSE
| Obtain administrative credentials for Applicaitons to enable SCIM integration (if applicable) | FALSE
| Obtain administrative credentials for HRIS (if applicable) | FALSE
| Obtain credentials for Super Admin (GWS) and-or Global Admin (MS 365) (if applicable) | FALSE
| Know the naming scheme of User accounts* on devices (laptops, desktops, servers) (if applicable) | FALSE
| Create an Apple Business Manager account with Apple.com if you plan to use JumpCloud's DEP and zero touch (if applicable) | FALSE
* Profile names must be unique across the organization and be the same between the device local username and the JumpCloud username.
| Task Name | Documentation | Admin Portal URL | Task Owner | Task Complete | Task Start Date | Task Complete Date | Notes
| Preparation Work |  |  |  |  | MM/DD/YY | MM/DD/YY
0.01 | Get Access to JumpCloud Admin Portal with Administrator Account | JCU: Intro to Admin Portal | JumpCloud Admin Portal |  | FALSE
0.02 | Bookmark the JumpCloud Admin Portal |  |  |  | FALSE
0.03 | Log into Admin Portal with your JumpCloud Admin Account | JumpCloud Admin Portal Login |  |  | FALSE
0.04 | Access Support KB Portal | JumpCloud Support Center | Support Page |  | FALSE
0.05 | Learn how to create a Support Case with JumpCloud in the Admin Portal | Contacting JumpCloud Support | Submit a Support Ticket |  | FALSE
0.06 | Find Organizational Settings | Admin Portal Org Settings | Org Settings |  | FALSE
0.07 | Name your Organization |  |  |  | FALSE
0.08 | Enter the primary admin's contact information |  |  |  | FALSE
0.09 | Upload company logo |  |  |  | FALSE
0.1 | Review the JumpCloud Admin portal layout |  |  |  | FALSE
0.11 | Educate Users on upcoming implementation of JumpCloud | Email templates for Educating New Users |  |  | FALSE
Preparation Milestones Complete
Phase 1 - Tour the JumpCloud Admin Portal
Pre | Inform Company that you will be implementing JumpCloud. Let them know what it is and how it affects them. | Email templates for Educating New Users |  |  | FALSE
1 | Find User Security Settings | User Security Settings | User Security Settings |  | FALSE
1.1 | Configure password complexity |  |  |  | FALSE
1.2 | Configure password aging |  |  |  | FALSE
1.3 | Configure password lockout |  |  |  | FALSE
1.4 | Configure User Portal Session Duration |  |  |  | FALSE
1.5 | Configure MFA Settings & Options | JumpCloud MFA Guide | MFA Configurations |  | FALSE
1.6 | Invite IT staff as JumpCloud administrators (Administrator accounts are separate from User accounts) | Managing JumpCloud Admins |  |  | FALSE
Phase 1 Milestones Complete
Phase 2 - Users
Pre | Inform Users that you are starting the project by creating JumpCloud Accounts for them. | Email templates for Educating New Users |  |  | FALSE
2 | Obtain cloud directory Admin credentials |  |  |  | FALSE
2.1 | Navigate to Cloud Directories Menu | Office 365 G Suite | Cloud Directories |  | FALSE
2.1.1 | Create a new Directory, and provide a display name |  |  |  | FALSE
2.1.2 | Utilize the cloud directories Admin credentials already obtained to sync with JumpCloud |  |  |  | FALSE
2.1.3 | Navigate to Users in JumpCloud Admin portal |  |  |  | FALSE
2.1.4 | Import Users (several different options) | Import Office 365 User Import G Suite User Import Users via CSV |  |  | FALSE
2.2 | Navigate to Users menu in JumpCloud Admin portal |  | Users |  | FALSE
2.2.1 | Bind the User to their Directory Sync. JumpCloud will become authoritative over their synced M365/GWS account. | Binding user to Office 365 Binding user to G Suite |  |  | FALSE
2.2.2 | The user will receive a Get Started email requiring them to set a JumpCloud password, in turn updating thier cloud directory password |  |  |  | FALSE
2.2.3 | The user will become active within JumpCloud once they've set a password from their welcome email in the previous step. |  |  |  | FALSE
2.3 | Create User Groups to align with org layout and requirements | Getting Started: Groups | User Groups |  | FALSE
2.3.1 | Assign Users to their respective User Group(s) |  |  |  | FALSE
2.4 | Enroll Users in MFA | Configuring MFA for User Accounts | MFA Configurations |  | FALSE
Phase 2 Milestone Complete
Phase 3 - Devices
Pre | Inform Users that their devices and local device accounts will be enrolled in JumpCloud via the JumpCloud Agent install | Email templates for Educating New Users |  |  | FALSE
3 | Identify initial Devices to test deployment methods |  |  |  | FALSE
3.1 | Install Agent on Devices | Manually Installing Agent Installing Agent via CLI Allow Agent Install from User Portal | Devices |  | FALSE
3.1.1 | Required: Ensure Devices Local Account Username match JumpCloud Username | Naming Conventions for Users Finding Local Device Account Names | Users |  | FALSE
3.1.2 | Either change local account name on device to match JumpCloud username or Set JumpCloud User's "Local Account Name" attribute to match the local device account name | Changing Existing Local Device Usernames Using Local Account Name Attribute |  |  | FALSE
3.2 | MacOS Monterey Only: You must grant Full Disk Access to jumpcloud-agent before it will communicate with JumpCloud | Granting Full Disk Access to JumpCloud Agent for MacOS Monterey | On Local Device |  | FALSE
3.3. | For AD Migrations Only: Utilize ADMU utility to convert any AD or AzureAD bound device and profile. ADMU to be executed locally on each device. (if applicable) | Getting Started: ADMU | On Local Device |  | FALSE
3.4 | Assign Users to their respective devices | Taking over Local Device Accounts with JumpCloud Connecting Users to Windows Devices Connecting Users to macOS Devices Connecting Users to Linux Devices | Devices |  | FALSE
3.5 | MacOS Only: Register JumpCloud as your MDM (if applicable) | Setting up MDM | MDM |  | FALSE
3.5.1 | MacOS Only: Connect your ABM account with JumpCloud MDM | Configuring Automated Device Enrollment |  |  | FALSE
3.5.2 | MacOS Only: Enroll Devices into MDM using Mac MDM policy | Enrolling Devices in MDM |  |  | FALSE
3.5.3 | MacOS Only: Local User approve MDM enrollment on Device | Enrolling Devices in MDM with User Approval | On Local Device |  | FALSE
3.6 | Create Device Groups to align with org security policies, departments, or location | Getting Started: Groups | Device Groups |  | FALSE
3.6.1 | Assign Devices to their respective device groups |  |  |  | FALSE
3.7 | Configure & Test Commands (if applicable) | Getting Started: Commands | Commands |  | FALSE
3.8 | Enable MFA for Devices | Configuring MFA for Devices | Devices |  | FALSE
3.9 | Configure Device Configurations/Policies for Mac, Windows, & Linux | Getting Started: Configurations (Policies) | Configurations (Policies) |  | FALSE
3.9.1 | Configure Full Disk Encrpytion for Mac & Windows | Configure FileVault2 for macOS Configure BitLocker for Windows |  |  | FALSE
3.9.2 | Enable & configure SSH key access for Linux devices | Using SSH Keys within JumpCloud JumpCloud sshd configuraiton | Devices |  | FALSE
Phase 3 Milestone Complete
Phase 4 - SSO
Pre | Notify Users that you are going to be redirecting all logins from X applications to JumpCloud starting on X date. | Email templates for Educating New Users |  |  | FALSE
Pre | Ensure all users that need the application are imported and activated with a valid password before starting anything within the SSO Phase |  | Users |  | FALSE
4 | Configure SAML app integration (if applicable) | Getting Started: Applications | SSO |  | FALSE
4.1 | Configure JIT app integration (if applicable) | SAML Supported JIT Provisioning |  |  | FALSE
4.2 | Configure SCIM app integration (if applicable) | JumpCloud Identity Management Connectors |  |  | FALSE
4.3 | Bind User Groups to the SSO Application(s) | Getting Started: Applications |  |  | FALSE
4.4 | Repeat for all of your companies SSO Applications |  |  |  | FALSE
Phase 4 Milestone Complete